## Sheet1
Date | From | To | Document | Notes
Current License and Amendments
1994-10-18 | FERC | RFPC | Order Issuing New License
2010-07-28 | FERC | RFH | Order Amending License
2019-03-26 | FERC | RFH | Order Amending License Article 406
2019-03-27 | FERC | RFH | Errata Notice for Order Amending License Article 406
2021-06-03 | FERC | RFH | Order Amending License to Include Battery System
Relicensing1
2019-09-27 | RFH | FERC | Notice of Intent to File Application for a New License and Pre-Application Document | Exhibit F drawings filed with FERC as CEII
2019-11-19 | FERC | - | Scoping Document 1
2020-01-03 | FERC | - | Transcript of 12/17/2019 Daytime Public Scoping Meeting
2020-01-03 | FERC | - | Transcript of 12/17/2019 Evening Public Scoping Meeting
2020-01-14 | RFH | FERC | 1989 Field Investigations at the Bypassed Reaches of the Rumford Falls Project
2020-02-27 | FERC | - | Scoping Document 2 Not Warranted
2020-03-10 | RFH | FERC | Proposed Study Plan
2020-07-07 | RFH | FERC | Revised Study Plan
2020-07-27 | MDEP | RFH | Email regarding MDEP site visit
2020-08-06 | FERC | RFH | Study Plan Determination
2020-10-30 | RFH | FERC | Quarterly Study Progress Report
2021-01-29 | RFH | FERC | Quarterly Study Progress Report
2021-04-08 | RFH | FERC | Notification of Postponement of the Recreation Study and Angler Creel Survey Due to Continued COVID-19 Pandemic
2021-04-30 | RFH | FERC | Quarterly Study Progress Report
2021-08-06 | RFH | FERC | Initial Study Report
2021-09-03 | RFH | FERC | Initial Study Report Meeting Summary
2021-10-29 | RFH | FERC | Quarterly Study Progress Report
2022-01-31 | RFH | FERC | Quarterly Study Progress Report
2022-04-29 | RFH | FERC | Quarterly Study Progress Report
2022-05-02 | RFH | FERC | Draft License Application
2022-08-05 | RFH | FERC | Updated Study Report
2022-09-06 | RFH | FERC | Updated Study Report Meeting Summary
2022-09-29 | RFH | FERC | Final License Application | Exhibit F drawings filed with FERC as CEII
2022-10-31 | FERC | RFH | Request for Additional Information
2022-11-21 | FERC | RFH | Determination on Requests for Study Modifications
2023-03-06 | RFH | FERC | Additional Information Response | Exhibit F drawings filed with FERC as CEII
2023-03-30 | RFH | FERC | Recreation Study Report, Angler Creel Survey Report, and Additional Protection, Mitigation, and Enhancement Measures
2023-04-19 | RFH | FERC | Response to MDIFW Comments on the Final License Application
2023-05-11 | FERC | RFH | Request for Additional Information
2023-05-15 | Town of Rumford | FERC | Comments on Environmental Measures & Associated Studies
2023-05-16 | RFH | FERC | Response to FERC's Exhibit F & G Requests | 3 separate files; Exhibit F drawings filed with FERC as CEII
2023-05-17 | MBPL | FERC | Comment on Proposed Recreation and Aesthetic Environmental Measures, Addendum to Final License Application
2023-06-06 | RFH | FERC | Trophic Sampling Memorandum
2023-06-09 | RFH | FERC | Response to FERC Additional Information Request for the Recreation Study Report
2023-06-26 | FERC | - | Notice of Application Accepted for Filing, Soliciting Motions to Intervene And Protests, Ready for Environmental Analysis, and Soliciting Comments, Recommendations, Preliminary Terms and Conditions, and Preliminary Fishway Prescriptions
2023-07-05 | Brie Weisman | FERC | Comments on recreation opportunities
2023-07-14 | Town of Rumford | FERC | Comments on RFH's Response to Commission's Additional Information Request
1 Letters, comments, and correspondence with stakeholders are included in the FLA, as well as other relicensing documents, and therefore, are not individually included. Stakeholder comments and letters that were filed with FERC after RFH filed the FLA are included, unless they were referenced or included in a subsequent filing.